# Initial project plan
    The first and most important part of this application is a search engine called Elasticsearch. It is the core technology which needs to be installed and properly set up for the needs of this application. This search engine is not particularly developed for searching in Latin or Middle Scots languages and therefore it will require more time to tune it up.
    The second important part of the application is relational database. Based on research was made the decision to use PostgreSQL. It is well known database with great performance and it will be used to store original XML files, credentials, images and privileges.
    The third thing which is required to be done is a module which will provide translation of XML documents to JSON. The reason is that Elasticsearch is natively used for searching inside JSON files and not XML which will be used. In parallel RSpec tests need to be written for this module.
    The fourth stage of the development includes creating all the modules in application layer. These modules provides the business logic for the application. Again in parallel with the development of these modules their tests in RSpec need to be written.
    The fifth part includes tuning up Elasticsearch and improving search results and potentially including Latin and Middle Scots thesaurus in to Elasticsearch. In this time the storage layer need to be done and tested.
    In the sixth stage, the whole application layer need to be finished and tested too. This also include XML to JSON module. Now it can begin the work on presentation layer and its tests.
    The seventh stage is about finishing the presentation layer and writing documentation.
Schedule
    The schedule for developing this application is 10 weeks.
1. Week: Installing dedicated Linux OS with Docker. Deploying separate linux containers with Elasticsearch, PostgreSQL and Ruby on Rails
2. Week: Setting up Elasticsearch, PostgreSQL, Ruby on Rails with Puma webserver
3. Week: Setting up Elasticsearch and writing storage layer modules with tests
4. Week: Testing Elasticsearch and finishing the work on storage layer. Start developing application layer and its tests.
5. Week: Tuning up Elasticsearch, finishing application layer and start working on presentation layer and design of the interface.
6. Week: Testing security and performance. Start writing documentation for admin users.
7. Week: Major meeting with client, receiving feedback on user interface and implementing changes.
8. Week: Writing documentation for end user.
9. Week: providing access to documents and testing Clarin API communication.
10. Week: Application will be delivered and  presented to the customers.
Milestones
- Setting up server with Docker, Elasticsearch, PostgreSQL and Ruby on Rails
- Elasticsearch is tuned up for this application purposes
- Pass all tests for storage layer
- Pass all tests for application layer
- Pass all tests for presentation layer
- Documentation for admin users is done
- Satisfied customer
Budget
Full Time Equivalent (FTE) cost of the whole team is £ 30k x 4 = £120 k/yr. As the team work for a specific fraction of the year (5 months) and as the team work Part-time (10/40 = 25% of the daily full time equivalent), the costs are £120,000 x 5/12 x 0,25 = £16,000.
Expense for labour is £16,000
- Expense for rent is £10,500
- Hardware depreciation is about £340
- Marketing and Advertising
  - Preparation of demonstrative materials
      - Total of 10 hours for 2 team members
  - Face-to-face meetings with potential customers
      - For each meeting: 2 hours for 2 team members
      Calculations:
                   ( 10 team members x 16 hourly rate x 2 hours ) + ( 2 team members x 16 hourly rate x 2 hours) = £ 384
- Accounting and Bookkeeping Services
  - £50 per mount x 6 mounts = £300
- Legal Advice
  - Budget £5 000.
- Travelling Costs
  - Budget £6 000.
Expenses together approximately £38,526. Reserve is going to be 20%. Therefore The total expenses with reserve included are approximately £46,229.